## History
FisherCat (RBC : AU1803, XBP : AU1805) Firmware History Release Note：
Date | MCU | RD Folder | State Machine Rev | DBC Rev | Bootloader Interface Rev | Firmware Rev | CheckSum | Formal Released to QE/Factory/SE/Lab/… | Firmware Update Info
2020-07-20 | dsPIC33EP128MC504 | T6_29ModifyV03 | Fisher Cat - BMS state Machine v1.8_20200527.vsd | 2020-05-06-SELiionBattery.dbc | NA | 44 |  | NO | Alan Merge new code of Jammar (Jammar_20200717_17 FW rev 044). Alan Fix previous lost while merging (Frank_20200713_1) : 1. Code about SMBUS_sortMinMaxTemperature(); //frank 7/8 2. Code about d_safeTime 7/29~8/4 frank 1. removed problem codes (interrupt rontine cause delay . (jason,Jammar)) 2. remove duplicate code in battery_manage_system.c 3. remove redunant code that change lostCommunication flag, could case learning preocess been interrupted (C/DFETturn off).
2020-07-14 | dsPIC33EP128MC504 | T6_29ModifyV01 | Fisher Cat - BMS state Machine v1.8_20200527.vsd | 2020-05-06-SELiionBattery.dbc | NA | 43 |  | NO | Merge Frank_20200713_1 and Jason_20200713_17
2020-07-14 | dsPIC33EP128MC504 | T6_29ModifyV01 | Fisher Cat - BMS state Machine v1.8_20200527.vsd | 2020-05-06-SELiionBattery.dbc | NA | 43 |  | NO | Merge Frank_20200713_1 and Jason_20200713_17
2020-07-13 | dsPIC33EP128MC504 | T6_26_ModifyV23 | Fisher Cat - BMS state Machine v1.8_20200527.vsd | 2020-05-06-SELiionBattery.dbc | NA | 42 |  | NO | 20200713 Jason Lin fix ODC current -120A
2020-07-10 | dsPIC33EP128MC504 | T6_26_ModifyV23 | Fisher Cat - BMS state Machine v1.8_20200527.vsd | 2020-05-06-SELiionBattery.dbc | NA | 41 |  | NO | 20200710 Jason Lin disable FirstDetection function for inproof
2020-07-08 | dsPIC33EP128MC504 | T6_26_ModifyV22 | Fisher Cat - BMS state Machine v1.8_20200527.vsd | 2020-05-06-SELiionBattery.dbc | NA | 40 |  | NO | frank 6/29 Avg value has problem need check
2020-07-08 | dsPIC33EP128MC504 | T6_26_ModifyV21 | Fisher Cat - BMS state Machine v1.8_20200527.vsd | 2020-05-06-SELiionBattery.dbc | NA | 39 |  | NO | 20200708 Jason Lin fix ODC current -150A change -120A
2020-07-07 | dsPIC33EP128MC504 | T6_26_ModifyV20 | Fisher Cat - BMS state Machine v1.8_20200527.vsd | 2020-05-06-SELiionBattery.dbc | NA | 38 |  | NO | 20200707 Jason Lin fix it
2020-06-30 | dsPIC33EP128MC504 | T6_26_ModifyV19 | Fisher Cat - BMS state Machine v1.8_20200527.vsd | 2020-05-06-SELiionBattery.dbc | NA | 37 |  | NO | 20200701 Jason Lin delete NO.32 & NO.41 20200701 Jason Lin add ODC function 20200701 Jason Lin change state diagram
2020-06-30 | dsPIC33EP128MC504 | T6_26_ModifyV16 | Fisher Cat - BMS state Machine v1.8_20200527.vsd | 2020-05-06-SELiionBattery.dbc | NA | 34 |  | NO | 20200630 Jason Lin LED pin define change
2020-06-26 | dsPIC33EP128MC504 | T6_26_ModifyV15 | Fisher Cat - BMS state Machine v1.8_20200527.vsd | 2020-05-06-SELiionBattery.dbc | NA | 33 |  | NO | 20200629 Jason Lin disable
2020-06-26 | dsPIC33EP128MC504 | T6_26_ModifyV14 | Fisher Cat - BMS state Machine v1.8_20200527.vsd | 2020-05-06-SELiionBattery.dbc | NA | 32 |  | YES | ESD Test
2020-06-26 | dsPIC33EP128MC504 | T6_26_ModifyV13 | Fisher Cat - BMS state Machine v1.8_20200527.vsd | 2020-05-06-SELiionBattery.dbc | NA | 31 |  | NO | 20200615 Jason Lin add pre-discharge function 20200618 Jason Lin modify
2020-06-22 | dsPIC33EP128MC504 | Jason_20200622_09 | Fisher Cat - BMS state Machine v1.8_20200527.vsd | 2020-05-06-SELiionBattery.dbc | NA | 29 |  | NO | 20200622 Jason Lin change 10 min => 10 sec
2020-06-19 | dsPIC33EP128MC504 | Alan_20200619_14 | Fisher Cat - BMS state Machine v1.8_20200527.vsd | 2020-05-06-SELiionBattery.dbc | NA | 29 |  | NO | Alan merge Jason_20200618_11 to current code (Improve FW of Class B Library for UL60730 test)
2020-06-18 | dsPIC33EP128MC504 | Jason_20200618_11 | Fisher Cat - BMS state Machine v1.8_20200527.vsd | 2020-05-06-SELiionBattery.dbc | NA | 29 |  | NO | 20200618 Jason Lin fix RB10 disable Pull Down function.
2020-06-17 | dsPIC33EP128MC504 | Frank_20200617_17 | Fisher Cat - BMS state Machine v1.8_20200527.vsd | 2020-05-06-SELiionBattery.dbc | NA | 028 |  | NO | 6/17 search "frank 6/' key word 1. add shutdown command to let gas-gauge turn off power safely through REG out pin of AFE. a. update all files in smbus folder b. update can_dbc.c, can_dbc.h 2. add clock failure safe function of pic33 update MyConfig.mc3 file, change configure word to enable this function update all files in MCC Generated Files folder update mcu_init.c, mcu_init.h in main_app folder 3. modify can_dbc_usages_vda.c and can_dbc_usages_mdat.c files in can folder to report FETs status
2020-06-15 | PIC18F46K80 | T6_28_ModifyV03 | Fisher Cat - BMS state Machine v1.8_20200527.vsd | 2020-05-06-SELiionBattery.dbc | NA | 028 | 4343 | YES | Release this FW rev 028 to SE for verification MDAT_Battery_status issue was fixed ( = APC : BatteryFrameStatus_BF flag) Fix init vol out bug. Is mainly for "Lost Communication Test"
2020-05-27 | PIC18F46K80 | T6_26_ModifyV08 | Fisher Cat - BMS state Machine v1.7_20200408.vsd | 2020-05-06-SELiionBattery.dbc | NA | 026 | 087F | YES | Release this FW rev 026 to Factory for DVT 25 pcs production add reset_all_status() in bmsidle add pSvdCmd->cmdChrgEnable = FALSE; d_cmdChargeEnable = FALSE; d_cmdDischargeEnable = FALSE; pSvdCmd->cmdDisChrgEnable = FALSE; in path No 15 change priority path no 12 > path no 64 ==> path no 64 > path no 12 fix CanDbcUtils_putDataIntoDcbFrame_MoveOneBit fix EOCV flag Fix init vol out bug. Is mainly for "Lost Communication Test"
2020-05-15 | PIC18F46K80 | T6_26_ModifyV02 | Fisher Cat - BMS state Machine v1.7_20200408.vsd | 2020-03-21-SELiionBattery.dbc | NA | 020 | EE36 | YES | Release this FW rev 020 to Factory for DVT 25 pcs production Fix bug of MDAT_TemperatureMax/ Min
2020-05-14 | PIC18F46K80 | T6_26_ModifyV01 | Fisher Cat - BMS state Machine v1.7_20200408.vsd | 2020-03-21-SELiionBattery.dbc | NA | 019 | EA87 | YES | Release this FW rev 019 to SE(APC) for testing. Modify the initial "Communication Loss" status by definition of SE.
2020-05-08 | PIC18F46K80 | T6_25_ModifyV01 | Fisher Cat - BMS state Machine v1.7_20200408.vsd | 2020-03-21-SELiionBattery.dbc | NA | 018 | F0B5 | YES | Release this FW rev 018 to Factory for DVT 25 pcs production Send 3 Sample Units (EVT 3 hardware sample + this FW by rev no = 017) to APC
2020-02-20 | PIC18F46K80 | T6_13_ModifyUARTPinForNewPCBA | Fisher Cat - BMS state Machine v0c - 20191212.pdf | 2019-08-27-SELiionBattery - IntelFormat.dbc | NA | 001 | E918 | YES | 23/Mar/2020 be released to for production test.
Note : FW rev example : Protocol/ Major/ Minor/ Build = 1011. It is shown by Major/ Minor/ Build = 011 via CanBus.